## Project Portfolio Fields
Project Portfolio Fields | Definition of Field | Drop-down or Free Text Guide | Remarks
Go to Latest Weekly Status Report | Link to Weekly Status Report Folder found in your Project Folder in the CIT PMO Sharepoint | Free Text | HyperLink
Go to Project Folder | Link to Project Folder in the CIT PMO Sharepoint | Free Text | HyperLink
Last Update Made | Date of update made by IT PM | Free Text | Date
Project Name | Project title given by the sponsor to the project | Free Text
Project Description and Business Benefit | Insert the target output and business outcome of the project once implemented | Free Text
Business Unit | Business Unit (BC, RRHI, DAVI, RBC, TGP, SSD, MNS, TRU, DIY, RBS, RSC, Savers, RA, Daiso, RSC, RSCI, RPI, RAC, RB, Super50, RLC, URC, PETSOC, ABSI, SMG, IGBS, RDS, HM) | Drop-down
Project Completion % | Percentage completion of the project based on project schedule or defined project milestones | Free Text | Percentage (%)
Project Health | RAG Status (Red-Amber-Green) | Drop-down
Project Status | Highlevel Project Status (In Pipeline - In Progress - Completed) | Drop-down
Start Date | Start date of project found in the project schedule (Day 1 of Initiating) | Free Text | Date
Go-Live Date | Business Go-Live date, when the product, service or result implemented will be used by the business | Free Text | Date
End Date | End date of project found in the project schedule (after project closeout and last signoff by sponsor) | Free Text | Date
Start Date (Rebaselined) | Rebaselined Project Start Date from Change Request, as approved by the Project Sponsor | Free Text | Date
Go-Live Date (Rebaselined) | Rebaselined Business Go-Live Date from Change Request, as approved by the Project Sponsor | Free Text | Date
End Date (Rebaselined) | Rebaselined Project End Date from Change Request, as approved by the Project Sponsor | Free Text | Date
Project Size | Project Size (Small-Medium-Large-Mega) | Drop-down | See sizing parameters sheet
Project Phase | Project Phase (1 - Initiating, 2 - Planning, 3 - Executing, 4 - Closing) | Drop-down
Project Sponsor | Project Sponsor Name | Free Text
IT Project Manager | IT Project Manager Name | Free Text
Value Theme | Business Value Drivers Category (Customer Service, System Upgrade, S4HANA, Productivity, Sales Growth, Savings, Stewardship, Productivity/Customer Service, and Productivity/Stewardship) | Drop-down
Sponsor Team | Sponsor Team (Analytics; Basis, Sap Security; It Security; Digital Workplace Group, Sharepoint, Productivity; Financials; Governance; Hr, Human Capital Management; Logistics; Manufacturing; Ccu Delivery; Store Systems; Supply Chain; Application Development; Infrastructure, Other) | Drop-down
IT COE Team | IT COE Team (Infrastructure & Store Support, Supply Chain, Data Analytics, CCU Delivery & Project Management, Application Development & Store Systems, Digital Transformation) | Drop-down
Remarks | Project Update: Achievements this reporting and Plan for the incoming weeks | Free Text
Budget Approved (Implem Svcs, Software, Hardware) | Approved Budget by Executive Budget Holder as aligned with Finance | Free Text | Financials
Actual Cost | Rolling Expense as of reporting date | Free Text | Financials
Cost at Completion | Projected Total Expense at the end of the project | Free Text | Financials
Savings in PHP | Projected Savings at the end of the project | Free Text
System Name | Impacting System / Application / Product | Free Text | Financials

## Project Health
Project Health | Definition of Value | Remarks | Remarks
Green | Within Target Baseline of Scope, Schedule and Financials as approved by Sponsor at the start of the project (based from Project Charter). No CRs and everything is on track. | Drop-down
Amber | At Risk of Missing Baseline of Scope, Schedule and Financials, there is a high potential of rebaselining of targets, expected CRs. | Drop-down
Red | Missed Baseline of Scope (added scope for change request) Missed Baseline of Schedule (as agreed within CIT, missed target Go-Live Date) Missed Financials (the Approved Budget is no longer sufficient to complete the project) | Drop-down
Not Applicable | Use this value for Not Started or In Pipeline and Completed or Done Projects | Drop-down

## Project Status
Project Status | Definition of Value | Remarks | Remarks
Completed | Done with the Business Go-Live and Post Go-Live / Hypercare project activities (Handover to Support and Post-Mortem) | Drop-down
In Progress | Started the project, project is approved by the Sponsor, and the Project Team have started the Project Planning activities | Drop-down
In Pipeline | The Project is still part of Roadmap / Backlog (Officially Not Started). Ongoing discovery and initiating activities. Project is not yet approved to start. No approved Project Charter. | Drop-down

## Project Phase
Project Phase | Definition of Value | Remarks | Remarks
1 - Initiating | Activities under this Phase: Project Chartering and Initiative Approval, Budget Approval | Drop-down | Completed Initiating = 10%
2 - Planning | Activities under this Phase: Requirements Gathering / Validation, Project Plan Establishment and Approval, Vendor Sourcing and All Procurement | Drop-down | Completed Planning = 30%
3 - Executing | Activities under this Phase: Resource Mobilization, Project Kickoff, Blueprint and Design of Solution, Develop / Buy Product, Unit Test, System Integration Test, User Acceptance Test, Pilot Deployment / Go-No Go Approval, Cutover for Main Deployment, Technical Go-Live, Business Go-Live, Hypercare / Warranty, Transition to BAU/Ops Support | Drop-down | Completed Executing = 80%
4 - Closing | Activities under this Phase: Project Closeout Report, Post Mortem | Drop-down | Completed Closing = 100%

## Proj Sizing Parameters
Project Size | Enhancement | Small | Medium | Large | MEGA
Functionalities Impacted | 1 Functionality | 1-3 Functionalities | Multiple functionalities | Multiple functionalities and /or systems | A Program (Multiple Projects), Multiple functionalities and/or systems
Complexity | Minimal to no intergration considerations | Minimal to no intergration considerations | Minimal to medium integration considerations | Medium to complex integration considerations | Medium to Complex integration considerations
Duration | 1-2 months | 2-3 months | 3-6 months | More than 6 months | 12 months or more
Team Size | <3 members | <5 members | 5-10 members | More than 10 members | More than 20 members

## Banners and their Bu
Banners | Business Unit
Appliances | Appliances
Benefit | Beauty
CledePeauBeaute | Beauty
Daiso | Mass Merchanise
DepartmentStore | Department Store
Easymart | Supermarket
Go-Cart | GoCart
HandyMan | DIY
Marketplace | Supermarket
MF | Department Store
NoBrand | Supermarket
PetLC | DIY
Rose | Drugstore
Savers | Appliances
Shiseido | Beauty
Shopwise | Supermarket
SSD | Drugstore
Super50 | Mass Merchanise
Supermarket | Supermarket
TGP | Drugstore
ToysRUs | Toys
TrueValue | DIY
UJ | Convenience Store

## Business Units
Business Unit
Supermarket
Drugstore
DIY
Convenience Store
Department Store
Appliances
Mass Merchanise
Toys
Beauty
GoCart

## Project Sizes
Project Sizes | Weight
Enhancement | 0
Small | 1
Medium | 2
Large | 3
Mega | 4