## Resource Mgt (hidden)
RESOURCE CAPACITY MANAGEMENT
Input Parameters custom to your BU or Banner
| PROJECT SIZE | COUNT OF PROJECTS | WEIGHT | CAPACITY IN % |  | Utilization Tagging | Utilization %
| MEGA | 1 | 80 | 80 |  | Over utilized | >120%
| LARGE | 1 | 50 | 50 |  | Utilized Fairly | 80-120%
| MEDIUM | 1 | 25 | 25 |  | Under Utilized | <80%
| SMALL | 1 | 15 | 15
| ENHANCEMENT | 1 | 10 | 10
| GROUP UTILIZATION REPORT |  |  |  |  | IT PROJECT MANAGER UTILIZATION REPORT
| BUSINESS UNIT | DRUG STORE
| BANNER | TGP |  |  |  | RESOURCE NAME | IT PM NAME HERE
| MONTH | JANUARY |  |  |  | MONTH | JANUARY
| PROJECT SIZE | COUNT OF PROJECTS | WEIGHT | CAPACITY IN % |  | PROJECT SIZE | COUNT OF PROJECTS | WEIGHT | CAPACITY IN %
| MEGA | 1 | 80 | 80 |  | MEGA | 0 | 80 | 0
| LARGE | 6 | 50 | 300 |  | LARGE | 1 | 50 | 50
| MEDIUM | 15 | 25 | 375 |  | MEDIUM | 2 | 25 | 50
| SMALL | 6 | 15 | 90 |  | SMALL | 1 | 15 | 15
| ENHANCEMENT | 0 | 10 | 0 |  | ENHANCEMENT | 0 | 10 | 0
|  |  |  | 845 |  |  |  |  | 115
|  |  | No of IT PMs | 6
|  |  | Grand Total | 140.8333
|  |  | Utilization Score | Over utilized |  |  |  | Utilization Score | Utilized Fairly
| GROUP UTILIZATION CHART - MONTHLY VIEW |  |  |  |  | IT PM UTILIZATION CHART - MONTHLY VIEW
| Month | No of IT PM | Acceptable Allocation | Actual Assignment |  | Month | Acceptable Allocation | Actual Assignment
| January | 6 | 720 | 846 |  | January | 120 | 115
| February | 6 | 720 | 540 |  | February | 120 | 130
| March | 6 | 720 | 570 |  | March | 120 | 130
| April | 6 | 720 | 660 |  | April | 120 | 90
| May | 6 | 720 | 780 |  | May | 120 | 90
| June | 6 | 720 | 840 |  | June | 120 | 90
| July | 6 | 720 | 540 |  | July | 120 | 85
| August | 6 | 720 | 540 |  | August | 120 | 80
| September | 6 | 720 | 420 |  | September | 120 | 70
| October | 6 | 720 | 390 |  | October | 120 | 70
| November | 6 | 720 | 420 |  | November | 120 | 65
| December | 6 | 720 | 540 |  | December | 120 | 90
Resource Name | 2023
| Jan | Feb | Mar | Apr | Jun | Jul | Aug | Sep | Oct | Dec

## RES MGT V1
RESOURCE CAPACITY MANAGEMENT
CAPACITY PARAMETERS |  |  |  | CAPACITY PARAMETERS |  |  |  |  | Note from CIT-PMO: In the Capacity Parameters Table found in the source file, update the 'Weight' values based on the assessment of project complexity and project size from your group.
PROJECT SIZE | COUNT OF PROJECTS | WEIGHT | CAPACITY IN % | Utilization Tagging | Utilization %
MEGA | 1 | 80 | 80 | Over utilized | >120%
LARGE | 1 | 50 | 50 | Utilized Fairly | 80-120%
MEDIUM | 1 | 25 | 25 | Under Utilized | <80%
SMALL | 1 | 15 | 15
ENHANCEMENT | 1 | 10 | 10
GROUP LEVEL VIEW
MONTHLY SUMMARY |  |  |  | YEARLY SUMMARY
GROUP UTILIZATION REPORT |  |  |  | GROUP UTILIZATION CHART - MONTHLY VIEW
BUSINESS UNIT | DRUG STORE |  |  | Month | No of IT PM | Acceptable Allocation MIN | Acceptable Allocation MAX | Actual Assignment
BANNER | TGP |  |  | January | 6 | 480 | 720 | 846
MONTH | JANUARY |  |  | February | 6 | 480 | 720 | 540
PROJECT SIZE | COUNT OF PROJECTS | WEIGHT | CAPACITY IN % | March | 6 | 480 | 720 | 570
MEGA | 1 | 80 | 80 | April | 6 | 480 | 720 | 660
LARGE | 6 | 50 | 300 | May | 6 | 480 | 720 | 780
MEDIUM | 15 | 25 | 375 | June | 6 | 480 | 720 | 840
SMALL | 6 | 15 | 90 | July | 6 | 480 | 720 | 540
ENHANCEMENT | 0 | 10 | 0 | August | 6 | 480 | 720 | 540
|  |  | 845 | September | 6 | 480 | 720 | 420
|  | No of IT PMs | 6 | October | 6 | 480 | 720 | 390
|  | Grand Total | 140.8333 | November | 6 | 480 | 720 | 420
|  | Utilization Score | Over utilized | December | 6 | 480 | 720 | 540
RESOURCE LEVEL VIEW
MONTHLY SUMMARY |  |  |  | YEARLY SUMMARY
IT PROJECT MANAGER UTILIZATION REPORT |  |  |  | IT PM UTILIZATION CHART - MONTHLY VIEW
|  |  |  | Month | No of IT PM | Acceptable Allocation MIN | Acceptable Allocation MAX | Actual Assignment
RESOURCE NAME | IT PM NAME HERE |  |  | January | 1 | 80 | 120 | 115
MONTH | JANUARY |  |  | February | 1 | 80 | 120 | 130
PROJECT SIZE | COUNT OF PROJECTS | WEIGHT | CAPACITY IN % | March | 1 | 80 | 120 | 130
MEGA | 0 | 80 | 0 | April | 1 | 80 | 120 | 90
LARGE | 1 | 50 | 50 | May | 1 | 80 | 120 | 90
MEDIUM | 2 | 25 | 50 | June | 1 | 80 | 120 | 90
SMALL | 1 | 15 | 15 | July | 1 | 80 | 120 | 85
ENHANCEMENT | 0 | 10 | 0 | August | 1 | 80 | 120 | 80
|  |  | 115 | September | 1 | 80 | 120 | 70
|  |  |  | October | 1 | 80 | 120 | 70
|  |  |  | November | 1 | 80 | 120 | 65
|  | Utilization Score | Utilized Fairly | December | 1 | 80 | 120 | 90